## Sheet1
Task | Start | Duration | End
Learning Solidity, JS, Ethers.js, MySQL | 2024-11-01 | 60 | 2024-12-31
Smart Contract Design & Deployment | 2025-01-01 | 25 | 2025-01-26
Frontend UI (HTML/CSS) | 2025-01-26 | 15 | 2025-02-10
Frontend Logic (JavaScript) | 2025-02-10 | 20 | 2025-03-02
Backend Development (Node.js, API) | 2025-03-01 | 20 | 2025-03-21
Blockchain Integration & Testing | 2025-03-21 | 20 | 2025-04-10
Admin Panel Features | 2025-04-10 | 15 | 2025-04-25
Vote Result Charts & Chart.js | 2025-04-25 | 10 | 2025-05-05
Validation & Security (MetaMask, Hashes) | 2025-05-05 | 10 | 2025-05-15
Final Testing & Debugging | 2025-05-15 | 7 | 2025-05-22
Documentation & Report Writing | 2025-05-22 | 10 | 2025-06-01
Final Presentation Preparation & Delivery | 2025-05-29 | 3 | 2025-06-01

## Sheet2
Task | Sum of Duration
Learning Solidity, JS, Ethers.js, MySQL | 60
Smart Contract Design & Deployment | 25
Frontend Logic (JavaScript) | 20
Backend Development (Node.js, API) | 20
Blockchain Integration & Testing | 20
Frontend UI (HTML/CSS) | 15
Admin Panel Features | 15
Documentation & Report Writing | 10
Validation & Security (MetaMask, Hashes) | 10
Vote Result Charts & Chart.js | 10
Final Testing & Debugging | 7
Final Presentation Preparation & Delivery | 3
Grand Total | 215